SSLM · Simple Solution, Low Maintenance

The Flow-to-Executive Translation Guide

Converting team flow signals into board-ready decisions — Enterprise Extension, Tier 3–4

Purpose. Teams and boards speak different languages. This guide gives the manager a consistent way to convert team-level flow telemetry into the five elements executives decide on, so boards govern in decision language rather than agile telemetry, and streams stay comparable across a portfolio.

What's inside: when this applies, the altitude break, the five executive elements, the translation table, the integrity check, roles, and how this connects to the Executive Stream One-Pager tool.

# 1. When this applies

This guide is part of the Enterprise Extension — it applies only once a value stream is governed above team level, by a board or portfolio function, not to a single Tier 1–2 project. Most projects using the core SSLM pack will never need it.

# 2. The altitude break

A hard boundary sits at the development/operational line. Below it, the manager works in flow — backlog, WIP, velocity, lead time. Above it, the executive sees only what those signals mean for a decision. Nothing team-level crosses the line raw.

# 3. The five executive elements

Alignment — which strategic objective this stream serves.

Confidence — RAG on the committed outcome and date, derived from flow.

Constraint — the one thing most limiting the stream, and the decision needed to clear it.

Value — whether released capability is landing in the operational stream.

Investment — whether spend is buying flow; fund, hold or stop.

# 4. The translation table

Read each row left to right: a signal the team sees becomes an element the executive decides on.

| Flow signal (below the line) | Executive element (above) | The decision it enables |
| --- | --- | --- |
| Velocity dropping, WIP climbing | Confidence | Clear the blockage, or reset the date |
| Backlog growing faster than throughput | Constraint | Re-prioritise the backlog, or fund more capacity |
| Lead time trending up over several cycles | Constraint | Authorise clearing a constraint |
| Stream's committed work no longer maps to a current strategic objective | Alignment | Re-scope the stream to the current strategy, or formally deprioritise it |
| Released capability shows no usage signal after go-live | Value | Investigate adoption blockers, or accept the capability isn't landing |
| Spend continues but throughput stays flat or falls | Investment | Hold, reduce, or stop funding until flow recovers |

# 5. The integrity check

The translation is only useful if it's honest. This is Principle 2 (Report the real colour) applied at value-stream altitude — before any element crosses the line:

It must trace to real flow evidence. A status that cannot be tied to a signal does not cross.

No smoothing. An amber that is really red is worse than no report — report the real colour.

One line of evidence per element, so an executive can trust it without seeing the telemetry.

The test: if a rating cannot be traced to a flow signal in one line, it is not ready to cross the line.

# 6. Roles

Manager (translator) — owns the flow layer, performs the translation, and owns the integrity of what crosses.

Executives — decide on the translated elements; they do not work in the flow layer.

Custodian — owns this guide and the standard mapping, so translation is consistent across streams.

# 7. Using the Executive Stream One-Pager

The manager derives the one-pager from the weekly flow, once per governance cycle — never re-authored. See the Executive Stream One-Pager Template in this folder.

# 8. Boundaries

No agile telemetry above the line — burn-downs, backlogs and velocity stay with the team.

Standard across streams — the same mapping is used everywhere, which is what makes streams comparable.

Don't pull team artefacts into the boardroom “to check” — that collapses the altitude break and returns the board to governing with telemetry.

The board decides in one language; the team delivers in another. The manager is the translator — and the translation must be honest.