## Template
SSLM · Simple Solution, Low Maintenance | [5 empty] | Idea Log · Template
Idea Log — Portfolio Idea & Change Intake Register
Every new idea and change idea, from submission on an Idea on a Page form through triage to its outcome.
How to use — one row per idea, in the order received. Assign the next Idea ID (format IDEA-NNN, e.g. IDEA-001) when the Idea on a Page form is logged — never reuse or renumber. If the idea is a Change idea, name the Project Reference (YYYY-NNN) it relates to. Update Status and Triage outcome as the idea moves through the intake process — see the Change Request & Idea Intake Guide. Once approved, record what it was developed into: a Business Case reference (new idea) or Change Request number (change idea).
Portfolio |  |  |  | Log owner |  |  |  | Reporting date
Idea ID | Title | Type (New/Change) | Related Project Reference | Submitter | Date submitted | Status | Triage outcome | Triage date | Developed into | Owner (PMO) | Comments

## Example
SSLM · Simple Solution, Low Maintenance | [5 empty] | Idea Log · Worked example
Idea Log — Portfolio Idea & Change Intake Register
Every new idea and change idea, from submission on an Idea on a Page form through triage to its outcome.
How to use — one row per idea, in the order received. Assign the next Idea ID (format IDEA-NNN, e.g. IDEA-001) when the Idea on a Page form is logged — never reuse or renumber. If the idea is a Change idea, name the Project Reference (YYYY-NNN) it relates to. Update Status and Triage outcome as the idea moves through the intake process — see the Change Request & Idea Intake Guide. Once approved, record what it was developed into: a Business Case reference (new idea) or Change Request number (change idea).
Portfolio | Enterprise Change Portfolio |  |  | Log owner | PMO |  |  | Reporting date | 30 Jun 2026
Idea ID | Title | Type (New/Change) | Related Project Reference | Submitter | Date submitted | Status | Triage outcome | Triage date | Developed into | Owner (PMO) | Comments
IDEA-001 | Customer self-service portal | New idea |  | R. Alvarez (Customer Ops) | 02 Apr 2026 | Approved | Approved – develop BC | 18 Apr 2026 | Business Case 2026-001 | A. Chen | Became Customer Portal Launch
IDEA-002 | Extend portal to cover billing disputes | Change idea | 2026-001 | M. Rivera (Sponsor) | 22 Jun 2026 | Approved | Approved – develop CR | 25 Jun 2026 | CR-01 | A. Chen | Raised once SSO scope was clearer
IDEA-003 | Self-service kiosk in branch lobby | New idea |  | Branch network | 10 May 2026 | Rejected | Rejected at screening | 17 May 2026 | — | A. Chen | Low strategic fit; duplicates portal scope
IDEA-004 | Automate SSO password reset flow | New idea |  | R. Okafor (IT) | 05 Jun 2026 | Screening | — |  | — | A. Chen | Awaiting PMO triage this cycle