## Template
SSLM · Simple Solution, Low Maintenance | [5 empty] | Benefit Register · Template
Benefit Register
One line per benefit — defined at Green Light, baselined before go-live, handed to the business, reviewed once at its horizon.
How to use — one row per Business Case benefit. Capture the baseline before go-live (miss this and the benefit can never be measured), name the outcomes owner and the review date, then hand over. At review, the business reads Actual from a BAU metric it already produces — no new measurement machinery. A cashable benefit only counts once someone acts to bank it.
Project |  | Reference |  | Outcomes accountable owner |  |  |  | Reporting date
Benefit | Strategic objective | Type | Cashable? | Baseline (value & date) | Target | Measure (BAU metric & report) | Outcomes owner | Review date | Dis-benefits | Actual at review | Status | Action to realise

## Example
SSLM · Simple Solution, Low Maintenance | [5 empty] | Benefit Register · Worked example
Benefit Register
One line per benefit — defined at Green Light, baselined before go-live, handed to the business, reviewed once at its horizon.
How to use — one row per Business Case benefit. Capture the baseline before go-live (miss this and the benefit can never be measured), name the outcomes owner and the review date, then hand over. At review, the business reads Actual from a BAU metric it already produces — no new measurement machinery. A cashable benefit only counts once someone acts to bank it.
Project | Customer Portal Launch | Reference |  | Outcomes accountable owner | M. Rivera |  |  | Reporting date | 30 Jun 2026
2026-001
Benefit | Strategic objective | Type | Cashable? | Baseline (value & date) | Target | Measure (BAU metric & report) | Outcomes owner | Review date | Dis-benefits | Actual at review | Status | Action to realise
Fewer inbound calls for the top 5 request types | Improve operating efficiency / self-service | Hard | Cashable | 4,200 calls/month — 2 wks before go-live | ≤ 2,900/month (−30%) | 'Calls — top 5 types' in the monthly ops report | Operations Manager | Go-live + 6 months (Jan 2027) | Watch for a rise in email / webform contacts | Pending review | Pending | Redeploy freed capacity to bank the saving
Faster resolution of common requests | Improve customer experience | Soft | Non-cashable | Avg 2 days to resolve | Same-day via self-service | 'Time to resolve' in the ops report | Operations Manager | Go-live + 6 months (Jan 2027) | — | Pending review | Pending | —