## Template
SSLM · Simple Solution, Low Maintenance |  |  | Cost & Resource Plan · Template
Cost & Resource Plan
Keep spend and resource visible and rolled up — the budget baseline, forecast, and resource schedule that sit behind the Weekly Update.
How to use — Part A tracks cost against the approved baseline; Part B tracks resource needs against the critical path. Actuals come from the finance system; the forecast is the Project Manager's view. Re-baselining either plan requires a Change Request.
Project |  | Reference |  | Reporting date
Part A — Cost Plan
Cost item / milestone | Budget | Actual to date | Forecast at completion | Variance | Status
Total
Part B — Resource Plan
Resource (role / skill) | Source (own / rent / automate) | When needed | On critical path? | Status

## Example
SSLM · Simple Solution, Low Maintenance |  |  | Cost & Resource Plan · Worked example
Cost & Resource Plan
Keep spend and resource visible and rolled up — the budget baseline, forecast, and resource schedule that sit behind the Weekly Update.
How to use — Part A tracks cost against the approved baseline; Part B tracks resource needs against the critical path. Actuals come from the finance system; the forecast is the Project Manager's view. Re-baselining either plan requires a Change Request.
Project | Customer Portal Launch | Reference | 2026-001 | Reporting date | 30 Jun 2026
Part A — Cost Plan
Cost item / milestone | Budget | Actual to date | Forecast at completion | Variance | Status
M1-M3 — Scoping, design, build | 180000 | 172000 | 178000 | -2000 | Green
M4 — SSO integration (vendor) | 45000 | 38000 | 52000 | 7000 | Amber
M5 — UAT | 30000 | 4000 | 30000 | 0 | Green
M6-M7 — Go-live & handover | 40000 | 0 | 40000 | 0 | Green
Total
Part B — Resource Plan
Resource (role / skill) | Source (own / rent / automate) | When needed | On critical path? | Status
Solution developer | Own (internal) | May-Jun 2026 | Yes | Green
SSO integration specialist | Rent (vendor) | Jun 2026 | Yes | Amber — vendor slippage
Business testers (UAT) | Own (internal, seconded) | Jun 2026 | No | Green