## Template
SSLM · Simple Solution, Low Maintenance |  |  | Design Principles Register · Template
Design Principles Register
Which Design Principles this project or platform decision has adopted, the complexity appetite behind it, and the measurable low-maintenance target checked at handover.
How to use — declare the complexity appetite and low-maintenance target at Green Light (see the Design Principles Guide). Mark each principle Adopted, Not adopted, Partial, or N/A, and how it's applied. Any deviation from a ratified principle is an Exception, recorded here and approved at SteerCo or a design authority. Optional domain clusters are picked up only when the project triggers them — mark untriggered ones N/A (as the worked example does) or remove them. Check the low-maintenance target at closure, alongside benefits.
Project |  | Reference |  | Reporting date
Complexity appetite declared |  |  |  | Rationale
Low-maintenance target |  |  |  | Status at handover
Principle | Cluster | Adopted? (Y/N/Partial) | How applied on this project | Exception? (Y/N) | Exception rationale | Exception approved by & date | Notes
Buy over build | Simple Solution
One platform over best-of-breed | Simple Solution
Configure over customise | Simple Solution
Just enough, just in time | Simple Solution
Add on demand over big-bang | Simple Solution
Consolidate and stabilise | Low Maintenance
Rent expertise over hire | Low Maintenance
Automate over manual | Low Maintenance
Total cost of ownership over upfront cost | Low Maintenance
Design for minimal operational footprint | Low Maintenance
Reversible over locked-in | Low Maintenance
Adopt over adapt | Technology (optional)
Integrate over duplicate | Technology (optional)
Secure and resilient by design | Technology (optional)
Minimal data footprint | Technology (optional)
Design for the end user | Technology (optional)
Pay for use over pay for capacity | Cost & Commercial (optional)
Opex over capex | Cost & Commercial (optional)
Cashable over stranded | Cost & Commercial (optional)
Single source of truth | Data & Information (optional)
Capture once, use many | Data & Information (optional)
Open formats over proprietary | Data & Information (optional)
Quality at source | Data & Information (optional)
Least privilege | Security, Privacy & Compliance (optional)
Compliance by design | Security, Privacy & Compliance (optional)
Auditability by design | Security, Privacy & Compliance (optional)
Data sovereignty | Security, Privacy & Compliance (optional)
Efficiency by design | Sustainability / ESG (optional)
Reuse over new | Sustainability / ESG (optional)
Measure and report footprint | Sustainability / ESG (optional)
Design for supportability | Service & Operations (optional)
Observability by design | Service & Operations (optional)
Self-service, automated operations | Service & Operations (optional)
Flexible over fixed | Property / Physical (optional)
Standard fit-out over bespoke | Property / Physical (optional)
Whole-of-life cost over build cost | Property / Physical (optional)

## Example
SSLM · Simple Solution, Low Maintenance |  |  | Design Principles Register · Example
Design Principles Register
Which Design Principles this project or platform decision has adopted, the complexity appetite behind it, and the measurable low-maintenance target checked at handover.
How to use — declare the complexity appetite and low-maintenance target at Green Light (see the Design Principles Guide). Mark each principle Adopted, Not adopted, Partial, or N/A, and how it's applied. Any deviation from a ratified principle is an Exception, recorded here and approved at SteerCo or a design authority. Optional domain clusters are picked up only when the project triggers them — mark untriggered ones N/A (as the worked example does) or remove them. Check the low-maintenance target at closure, alongside benefits.
Project | Customer Portal Launch | Reference | 2026-001 | Reporting date | 30 Jun 2026
Complexity appetite declared |  | Low |  | Rationale |  | Solo/small team; no external oversight beyond SteerCo; reduce ongoing support burden
Low-maintenance target |  | One platform (no new auth system); lowest run cost |  | Status at handover |  | Achieved
Principle | Cluster | Adopted? (Y/N/Partial) | How applied on this project | Exception? (Y/N) | Exception rationale | Exception approved by & date | Notes
Buy over build | Simple Solution | Y | Configured the existing platform's portal module rather than building bespoke | N
One platform over best-of-breed | Simple Solution | Y | Single SSO platform integrated rather than a bespoke authentication build | N
Configure over customise | Simple Solution | Y | Portal module configured, not custom-coded | N
Just enough, just in time | Simple Solution | Y | Self-service built for the top 5 request types only | N
Add on demand over big-bang | Simple Solution | Partial | Remaining request types deferred to a future phase | N
Consolidate and stabilise | Low Maintenance | Y | No additional platforms introduced | N
Rent expertise over hire | Low Maintenance | Y | SSO specialist contracted for the integration, not hired | N
Automate over manual | Low Maintenance | Partial | Reporting still manually compiled; automation deferred | N
Total cost of ownership over upfront cost | Low Maintenance | Y | Platform module chosen over cheaper bespoke build on TCO grounds | N
Design for minimal operational footprint | Low Maintenance | Y | One platform, no new system to run — see low-maintenance target above | N
Reversible over locked-in | Low Maintenance | Y | Local-auth fallback (CR-01) kept as verified rollback until SSO confirmed stable, then retired | N
Adopt over adapt | Technology (optional) | Y | Aligned portal self-service to the platform's standard module rather than reshaping it to the old process | N
Integrate over duplicate | Technology (optional) | Y | Single SSO identity source; the portal reads customer data via API rather than copying it | N
Secure and resilient by design | Technology (optional) | Y | SSO and access control designed in from Green Light; a portal availability target was set and tested | N
Minimal data footprint | Technology (optional) | Y | Only the customer records needed for the top-5 self-service requests were exposed; no bulk migration | N
Design for the end user | Technology (optional) | Y | Built for the top 5 request types; success measured by reduced inbound calls (see the Benefit Register) | N
Pay for use over pay for capacity | Cost & Commercial (optional) | Y | Portal runs on the existing SaaS platform's consumption model; no new fixed capacity bought | N
Opex over capex | Cost & Commercial (optional) | Y | Delivered as configuration on an existing platform (opex); no new capital hardware | N
Cashable over stranded | Cost & Commercial (optional) | Partial | Call-reduction saving identified; cashable only if freed capacity is redeployed (see the Benefit Register) | N
Single source of truth | Data & Information (optional) | Y | Portal reads customer records from the system of record via API; no separate copy | N
Capture once, use many | Data & Information (optional) | Y | A self-service request is captured once and reused by downstream processes | N
Open formats over proprietary | Data & Information (optional) | Partial | Standard APIs used; some platform-native formats remain | N
Quality at source | Data & Information (optional) | Y | Validation applied at portal entry before submission | N
Least privilege | Security, Privacy & Compliance (optional) | Y | Portal access scoped to the customer's own records via SSO roles | N
Compliance by design | Security, Privacy & Compliance (optional) | Y | Privacy obligations built into the data shown in self-service | N
Auditability by design | Security, Privacy & Compliance (optional) | Y | Access and changes logged for audit | N
Data sovereignty | Security, Privacy & Compliance (optional) | Y | Data held in the platform's existing approved region | N
Efficiency by design | Sustainability / ESG (optional) | N/A | Not triggered — no ESG mandate for this project | N
Reuse over new | Sustainability / ESG (optional) | N/A | Not triggered — no ESG mandate for this project | N
Measure and report footprint | Sustainability / ESG (optional) | N/A | Not triggered — no ESG mandate for this project | N
Design for supportability | Service & Operations (optional) | Y | Runbook and support ownership agreed at handover (M7) | N
Observability by design | Service & Operations (optional) | Partial | Platform monitoring in place; portal-specific alerts still being defined | N
Self-service, automated operations | Service & Operations (optional) | Y | Self-service portal reduces manual request handling | N
Flexible over fixed | Property / Physical (optional) | N/A | Not triggered — no physical component | N
Standard fit-out over bespoke | Property / Physical (optional) | N/A | Not triggered — no physical component | N
Whole-of-life cost over build cost | Property / Physical (optional) | N/A | Not triggered — no physical component | N

## Technical Debt Log
SSLM · Simple Solution, Low Maintenance |  |  | Technical Debt Log
Technical Debt Log
Complexity knowingly added by an approved Design Principles exception, tracked until it's retired or accepted permanently.
How to use — one row per exception logged in the Design Principles Register that adds lasting complexity. Review at each stage gate (see the SOP, §1.5/§2.1); close out or re-approve at each review. An exception that's still open at closure carries forward as a known limitation in the Closure & Handover Report.
Project |  | Reference |  | Reporting date
Debt ID | Related Exception (Principle) | Description of complexity added | Added on | Next review date | Status (Open/Retired) | Owner | Notes
TD-001 | Reversible over locked-in | Local-auth fallback (CR-01) kept temporarily alongside SSO as a rollback path | 18 Jun 2026 | Go-Live | Open | A. Chen | Retire once SSO confirmed stable for one full reporting cycle