## Project Summary · Template
SSLM · Simple Solution, Low Maintenance |  |  | Monthly Project Summary · Template
Monthly Project Summary
One project's monthly position — synthesised from that month's weekly reports. Feeds the Portfolio Roll-up to the Board of Management.
How to use — prepared once a month by the Project Manager, drawing on the month's Weekly Reports and open RAID items. Reference must match the number assigned on the PTIP.
Project |  | Reference (YYYY-NNN) |  | Reporting month
Prepared by |  | RAG status |  | Trend
Dimension | Summary
Milestone status (this month)
Budget status ($ actual vs forecast, variance)
Key achievements this month
Key risks/issues escalated to the Board (top 3 by priority; stays listed until resolved)
Decisions needed from the Board
Focus for next month

## Project Summary · Example
SSLM · Simple Solution, Low Maintenance |  |  |  | Monthly Project Summary · Worked example
Monthly Project Summary
One project's monthly position — synthesised from that month's weekly reports. Feeds the Portfolio Roll-up to the Board of Management.
How to use — prepared once a month by the Project Manager, drawing on the month's Weekly Reports and open RAID items. Reference must match the number assigned on the PTIP.
Project | Customer Portal Launch | Reference (YYYY-NNN) | 2026-001 |  | Reporting month | Jun 2026
Prepared by | A. Chen | RAG status | Amber |  | Trend | Stable
Dimension | Summary
Milestone status (this month) | M1-M3 complete; M4 (SSO integration) delayed — vendor slippage.
Budget status ($ actual vs forecast, variance) | $310k actual vs $340k forecast to date; on budget overall.
Key achievements this month | Requirements, design and build phases signed off; UAT prep underway.
Key risks/issues escalated to the Board (top 3 by priority; stays listed until resolved) | Vendor slippage on SSO integration risks Go-Live date (see R-linked CR-01).
Decisions needed from the Board | Approve 2-week schedule extension for Go-Live (linked to CR-01).
Focus for next month | Complete SSO integration; begin UAT.

## Portfolio Roll-up · Template
SSLM · Simple Solution, Low Maintenance | [5 empty] | Portfolio Roll-up to BoM · Template
Monthly Report to BoM
One row per active initiative, compiled by the PMO from each project's Monthly Project Summary.
How to use — the PMO compiles this from the month's Project Summaries. Reference and Project columns should match the PTIP exactly, so the Board can trace any line back to its portfolio entry.
Portfolio |  |  |  | Reporting month |  |  |  | Prepared by
Reference | Initiative / project | RAG | Trend | Milestone status | Budget status | Key escalation | Decision needed | Owner

## Portfolio Roll-up · Example
SSLM · Simple Solution, Low Maintenance | [5 empty] | Portfolio Roll-up to BoM · Worked example
Monthly Report to BoM
One row per active initiative, compiled by the PMO from each project's Monthly Project Summary.
How to use — the PMO compiles this from the month's Project Summaries. Reference and Project columns should match the PTIP exactly, so the Board can trace any line back to its portfolio entry.
Portfolio | Enterprise Change Portfolio |  |  | Reporting month | Jun 2026 |  |  | Prepared by | PMO
Reference | Initiative / project | RAG | Trend | Milestone status | Budget status | Key escalation | Decision needed | Owner
2026-001 | Customer Portal Launch | Amber | Stable | M4 (SSO) delayed; M1-M3 complete | On budget ($310k/$340k) | Vendor slippage risks Go-Live date | Approve 2-week schedule extension | M. Rivera
2026-002 | Billing system upgrade | Green | Improved | On track, all milestones green | Under budget | None | None | Finance lead
2026-003 | Data warehouse consolidation | Red | Declined | Design phase blocked | Over budget (+12%) | Vendor dispute over scope | Decide: renegotiate or re-scope | IT lead