## Template
SSLM · Simple Solution, Low Maintenance | Project Health-Check · Template
Project Health-Check
A light, repeatable assurance instrument — the assurance equivalent of the weekly report.
How to use — score each dimension 1–5 for completeness and note the evidence. It checks whether the project is being run properly, not what it is delivering. Completeness: 1 not started · 2 started · 3 half complete · 4 mostly complete · 5 complete.
Project
Reviewer
Review date
Reference
Dimension | Score (1–5) | Comment / evidence
Objectives and scope defined
Plan and schedule
Risk managed (RAID)
Quality standards and QA
Resourcing (people and budget)
Monitoring and control
Stakeholder communication
Documentation and decisions
Issue and change control
Benefits and closure readiness
Continuous improvement / lessons
Overall (average)

## Example
SSLM · Simple Solution, Low Maintenance | Project Health-Check · Worked example
Project Health-Check
A light, repeatable assurance instrument — the assurance equivalent of the weekly report.
How to use — score each dimension 1–5 for completeness and note the evidence. It checks whether the project is being run properly, not what it is delivering. Completeness: 1 not started · 2 started · 3 half complete · 4 mostly complete · 5 complete.
Project | Customer Portal Launch
Reviewer | Independent reviewer (self-check)
Review date | 30 Jun 2026
Reference | 2026-001
Dimension | Score (1–5) | Comment / evidence
Objectives and scope defined | 5 | Scope baselined and signed off (M1).
Plan and schedule | 4 | Plan maintained; SSO slippage flagged.
Risk managed (RAID) | 4 | RAID live; risks linked to milestones.
Quality standards and QA | 3 | QA defined; UAT plan drafted.
Resourcing (people and budget) | 3 | Core team in place; vendor dependency open.
Monitoring and control | 4 | Weekly report composed each cycle.
Stakeholder communication | 4 | Stakeholder map and comms plan in use.
Documentation and decisions | 3 | Decisions logged; some records to tidy.
Issue and change control | 4 | CR process live (CR-01 approved).
Benefits and closure readiness | 2 | Benefit baseline not yet captured — due before go-live.
Continuous improvement / lessons | 3 | Lessons captured at each stage boundary.
Overall (average) |  | Overall completeness across dimensions