## Template
SSLM · Simple Solution, Low Maintenance |  |  | Risk Assessment · Template
Risk Assessment
How well is each step of the risk management process being applied on this project? Pairs with the Risk & Assurance Approach Guide.
How to use — score each step 1 (not happening) to 5 (fully embedded), and record how it is actually being done on this project. Reference must match the number assigned on the PTIP, format YYYY-NNN, e.g. 2026-001.
Project |  | Reference |  | Review date
Risk process step | What good looks like | Score (1-5) | How it's being applied on this project
Risk Identification | Form a cross-functional team (functional, technical, key leaders, vendors) to identify potential risks through structured brainstorming.
Risk Assessment | Assess each risk's potential impact and likelihood. Categorise as technical, organisational, operational, security, or external.
Risk Quantification | Assign numerical values where possible to rank risks by severity, using a risk matrix or scoring system.
Risk Mitigation | Develop mitigation strategies and contingency plans for high-priority risks; assign an owner to each action.
Risk Monitoring | Review and reassess risks on a regular schedule throughout the project; adapt the strategy as new risks emerge.
Risk Communication | Keep stakeholders informed of risks and mitigation efforts; keep channels open for reporting new or changed risks.
Risk Documentation | Maintain the RAID Log with current status, mitigation plans, and responsible parties for every risk.
Contingency Planning | Maintain specific contingency actions and backup arrangements for high-impact risks.
Risk Reporting | Provide regular risk status to the Project Sponsor, stakeholders, and SteerCo as part of standard reporting.
Lessons Learned | Review the risk management process at stage boundaries or closure and log insights for future projects.

## Example
SSLM · Simple Solution, Low Maintenance |  |  | Risk Assessment · Worked example
Risk Assessment
How well is each step of the risk management process being applied on this project? Pairs with the Risk & Assurance Approach Guide.
How to use — score each step 1 (not happening) to 5 (fully embedded), and record how it is actually being done on this project. Reference must match the number assigned on the PTIP, format YYYY-NNN, e.g. 2026-001.
Project | Customer Portal Launch | Reference | 2026-001 | Review date | 30 Jun 2026
Risk process step | What good looks like | Score (1-5) | How it's being applied on this project
Risk Identification | Form a cross-functional team (functional, technical, key leaders, vendors) to identify potential risks through structured brainstorming. | 5 | Initial risks captured during scoping with the project team and key stakeholders; logged in the RAID Log as identified.
Risk Assessment | Assess each risk's potential impact and likelihood. Categorise as technical, organisational, operational, security, or external. | 4 | Each risk categorised (technical, organisational, operational, external); reviewed at each SteerCo.
Risk Quantification | Assign numerical values where possible to rank risks by severity, using a risk matrix or scoring system. | 4 | Impact and Probability rated High/Medium/Low per risk; a $ value assigned where estimable.
Risk Mitigation | Develop mitigation strategies and contingency plans for high-priority risks; assign an owner to each action. | 4 | Each RAID item has a mitigation plan and named owner; escalated to a Change Request if it affects baseline.
Risk Monitoring | Review and reassess risks on a regular schedule throughout the project; adapt the strategy as new risks emerge. | 4 | Risks reviewed weekly by the PM and ahead of every SteerCo meeting.
Risk Communication | Keep stakeholders informed of risks and mitigation efforts; keep channels open for reporting new or changed risks. | 4 | Key risks summarised in the Weekly Update; open items visible to the full project team.
Risk Documentation | Maintain the RAID Log with current status, mitigation plans, and responsible parties for every risk. | 5 | RAID Log maintained as the single risk register; updated from team and stakeholder meetings.
Contingency Planning | Maintain specific contingency actions and backup arrangements for high-impact risks. | 3 | Contingency actions documented for the two highest-impact risks; not yet defined for lower-priority items.
Risk Reporting | Provide regular risk status to the Project Sponsor, stakeholders, and SteerCo as part of standard reporting. | 4 | Risk status reported monthly to the Project Sponsor and at every SteerCo meeting.
Lessons Learned | Review the risk management process at stage boundaries or closure and log insights for future projects. | 3 | Captured at each stage boundary; consolidated review still pending for this project.