## Template
SSLM · Simple Solution, Low Maintenance |  |  | Vendor Register · Template
Vendor Register
One row per vendor engagement — scope, dates, criticality, and performance, linked back to the RAID items and milestones that vendor touches.
How to use — add a vendor at onboarding (see the Vendor & Procurement Management Guide). Review performance RAG at a cadence matched to criticality. Any change to scope, cost, or timeline is a Change Request, logged in the CR column.
Project |  | Reference |  | Reporting date
Vendor | Scope summary | Contract start | Contract end | Key contact | Criticality (H/M/L) | Performance (RAG) | Related milestone(s) | Related RAID item(s) | Related CR | Comments

## Example
SSLM · Simple Solution, Low Maintenance |  |  | Vendor Register · Worked example
Vendor Register
One row per vendor engagement — scope, dates, criticality, and performance, linked back to the RAID items and milestones that vendor touches.
How to use — add a vendor at onboarding (see the Vendor & Procurement Management Guide). Review performance RAG at a cadence matched to criticality. Any change to scope, cost, or timeline is a Change Request, logged in the CR column.
Project | Customer Portal Launch | Reference | 2026-001 | Reporting date | 30 Jun 2026
Vendor | Scope summary | Contract start | Contract end | Key contact | Criticality (H/M/L) | Performance (RAG) | Related milestone(s) | Related RAID item(s) | Related CR | Comments
Identity solutions vendor | SSO / identity provider integration for the customer portal | 01 May 2026 | 31 Jul 2026 | Account manager, vendor side | High | Amber | M4 | D001, I001, R001 | — | Integration running behind; weekly check-in added for the delivery window.
Content migration contractor | One-off migration of existing help-centre content into the new portal | 15 May 2026 | 20 Jun 2026 | Lead contractor | Medium | Green | M3 | AS001 | — | On track; final content batch due before UAT.